## Summary
ReviewReply Enterprise
Bug & Feature Tracker — v1.0 · Aug 2026 · Prepared by Z.ai Strategic Engineering
PROJECT HEALTH
Total Issues | 82 | Across all severities
P0 Critical | 5 | Production blockers — fix immediately
P1 Important | 18 | Critical for launch
P2 Moderate | 32 | Fix within 30 days of launch
P3 Minor | 27 | Cosmetic / tech debt
Feature Modules | 10 | Proposed enterprise modules
Total Investment | $345k | 24-week rebuild
Timeline | 24 wks | Phase 0 → Phase 6
PHASE PROGRESS
Phase | Focus | Timeline | Status | Budget
Phase 0 | Stabilization | Week 1–2 | TODO | $15k
Phase 1 | Design System | Week 3–5 | Planned | $45k
Phase 2 | Auth & Multi-Tenant | Week 6–7 | Planned | $30k
Phase 3 | Core Module Rebuild | Week 8–11 | Planned | $60k
Phase 4 | Enterprise Modules | Week 12–18 | Planned | $105k
Phase 5 | Automation & AI | Week 19–22 | Planned | $60k
Phase 6 | Compliance & Launch | Week 23–24 | Planned | $30k

## P0 Critical Bugs
P0 Critical Bugs — Production Blockers
These must be fixed before any user touches the app. Fix in Phase 0 (Week 1–2).
ID | Severity | Description | Location | Area | Phase | Owner | Status
FB-01 | P0 | OnboardingForm calls POST /api/businesses/[id]/connect/facebook — route does not exist. Every new user clicking 'Connect Facebook' gets a 404. | OnboardingForm.tsx:126 | Frontend | Phase 0 | Lead BE | TODO
FB-02 | P0 | Enterprise plan rejected by checkout/manage endpoints. BillingManager calls startCheckout('enterprise') but /api/billing/checkout rejects with if (plan !== 'starter' && plan !== 'pro'). | lib/integrations/stripe.ts | Backend | Phase 0 | Lead BE | TODO
BB-01 | P0 | /api/dev/trigger is unauthenticated — anyone on the internet can trigger any background job (mass SMS sending, AI generation, review polling). | app/api/dev/trigger/route.ts | Backend/Security | Phase 0 | Lead BE | TODO
BB-02 | P0 | No Stripe webhook handler exists. Checkout endpoint calls finalizeCheckout() directly, bypassing Stripe entirely and creating phantom subscriptions. | lib/integrations/stripe.ts | Backend/Billing | Phase 0 | Lead BE | TODO
BB-03 | P0 | /api/inngest has no signature verification — forged Inngest events are accepted, allowing arbitrary background job injection. | app/api/inngest/route.ts | Backend/Security | Phase 0 | Lead BE | TODO
BB-04 | P0 | Google postReply() throws unconditionally in real mode; fetchReviews() hardcodes accountId = '' — integration is non-functional. | lib/integrations/google-business-profile.ts | Backend/Integration | Phase 0 | Lead BE | TODO
BB-05 | P0 | Facebook postReply() throws unconditionally in real mode — integration is non-functional. | lib/integrations/facebook-graph.ts | Backend/Integration | Phase 0 | Lead BE | TODO
BB-06 | P0 | SupabaseStore.signIn() always throws 'not implemented in real mode' — auth is completely broken in production. | lib/supabase/supabase-store.ts | Backend/Auth | Phase 0 | Lead BE | TODO

## P1-P3 Bugs
P1 / P2 / P3 Bugs — Critical → Minor
P1 fix in Phase 0. P2 fix within 30 days of launch. P3 opportunistic.
ID | Severity | Description | Location | Area | Phase | Owner | Status
FB-03 | P1 | /api/billing/manage uses businesses[0] instead of getActiveBusiness() — multi-location users cancel/change the wrong business. | app/api/billing/manage/route.ts | Backend/Billing | Phase 0 | Lead BE | TODO
FB-04 | P1 | Duplicate <h1>Review Requests</h1> on /requests (page.tsx + RequestsManager.tsx both render it). | app/(app)/requests/page.tsx | Frontend/SEO | Phase 0 | Lead FE | TODO
FB-05 | P1 | No app/(marketing)/layout.tsx — every marketing page re-implements nav/footer; /vs/* and /privacy /terms are dead-end pages. | app/(marketing)/ | Frontend/IA | Phase 1 | Designer | TODO
FB-06 | P1 | No app/not-found.tsx, error.tsx, loading.tsx anywhere — Next.js defaults to plain white 404. | app/ | Frontend/UX | Phase 0 | Lead FE | TODO
FB-07 | P1 | Invalid Tailwind classes silently no-op: space-y-22, mb-22, duration-400, prose prose-invert. | multiple components | Frontend/Code | Phase 0 | Lead FE | TODO
BB-07 | P1 | organizations table RLS disabled entirely — any authed user can read any org's data. | supabase/migrations/0002_add_organizations.sql | Backend/Security | Phase 0 | Sec Eng | TODO
BB-08 | P1 | PII (customer_contact) stored as plain text despite data-handling policy mandate requiring encryption. | supabase/migrations/0001_init.sql | Backend/Security | Phase 0 | Sec Eng | TODO
BB-09 | P1 | AI_MODEL = 'claude-sonnet-4-6' is a non-existent Anthropic model identifier. First real API call will fail. | lib/ai/draft-reply.ts | Backend/AI | Phase 0 | Lead BE | TODO
BB-10 | P1 | No rate limiting anywhere — every endpoint can be abused (auth brute-force, AI cost abuse, SMS spam). | all of app/api/ | Backend/Security | Phase 0 | Lead BE | TODO
D-01 | P1 | No icon library — every icon is Unicode/emoji (★ ☆ ✓ → ● ◆ 🍕). Logo carousel uses 8 emoji as fake business logos. | multiple components | Design | Phase 1 | Designer | TODO
D-02 | P1 | No Framer Motion — all motion is CSS transition 0.2s ease. Missing spring physics, AnimatePresence, layout animations. | all components | Design/Motion | Phase 1 | Lead FE | TODO
D-03 | P1 | Placeholder content shipped — stat cards say 'Placeholder stat — replace with sourced figure'. | StatCounter.tsx | Design/Content | Phase 1 | Designer | TODO
D-04 | P1 | Login page has zero brand context — generic email/password form on plain background. | app/(marketing)/login/page.tsx | Design/UX | Phase 1 | Designer | TODO
D-05 | P1 | Marketing nav has no mobile hamburger menu — nav items overflow horizontally on mobile. | landing-page.html | Design/Responsive | Phase 1 | Lead FE | TODO
D-06 | P1 | No skeleton loaders — loading state is 'Saving…' text only. | all async pages | Design/UX | Phase 1 | Lead FE | TODO
D-07 | P1 | No empty-state illustrations — just plain text 'No reviews yet'. | all list pages | Design/UX | Phase 1 | Designer | TODO
D-08 | P1 | No modals/dialogs/dropdowns/toasts/tabs primitives — all hand-rolled or absent. | components/ | Design/System | Phase 1 | Lead FE | TODO
D-09 | P1 | No charts anywhere — multi-location org-dashboard is a raw <table>. | app/(app)/org-dashboard/page.tsx | Design/DataViz | Phase 1 | Lead FE | TODO
FB-08 | P2 | LogoCarousel uses 8 emoji-in-colored-squares as fake business logos. | LogoCarousel.tsx | Frontend/Content | Phase 1 | Designer | TODO
FB-09 | P2 | StatCounter shows 'Placeholder stat — replace with sourced figure' text. | StatCounter.tsx | Frontend/Content | Phase 1 | Designer | TODO
FB-10 | P2 | Login page has zero brand context — generic form. | app/(marketing)/login/page.tsx | Frontend/Design | Phase 1 | Designer | TODO
BB-11 | P2 | N+1 queries in 4 hot paths — iterate all businesses to find one review by ID. | lib/supabase/supabase-store.ts | Backend/Perf | Phase 0 | Lead BE | TODO
BB-12 | P2 | 0 Zod schemas despite zod being a dependency — no input validation anywhere. | all of app/api/ | Backend/Safety | Phase 0 | Lead BE | TODO
BB-13 | P2 | Mock data leaks into production path — connect/google/route.ts uses MOCK_GOOGLE_LOCATIONS with no isMockMode guard. | app/api/businesses/[id]/connect/google/route.ts | Backend | Phase 0 | Lead BE | TODO
BB-14 | P2 | 7 missing indexes on hot paths — reviews(business_id, created_at), review_requests(business_id, status), etc. | supabase/migrations/ | Backend/Perf | Phase 0 | Lead BE | TODO
BB-15 | P2 | autoPostIfEligible hardcodes token = 'mock-token' even in production path. | lib/integrations/index.ts | Backend | Phase 0 | Lead BE | TODO
BB-16 | P2 | No CSRF protection on route handlers — POST endpoints vulnerable to cross-site request forgery. | all of app/api/ | Backend/Security | Phase 0 | Sec Eng | TODO
D-10 | P2 | No dark mode — only light theme, despite brand being dark-friendly. | tailwind.config.ts | Design | Phase 1 | Lead FE | TODO
D-11 | P2 | No command palette (Cmd+K) — power users have no shortcut-driven navigation. | app/(app)/ | Design/UX | Phase 1 | Lead FE | TODO
D-12 | P2 | Mobile app nav is horizontal overflow scroll — no bottom tab bar. | app/(app)/layout.tsx | Design/Responsive | Phase 1 | Lead FE | TODO
D-13 | P2 | No toast notification system — save success/failure has no UI feedback. | components/ | Design/UX | Phase 1 | Lead FE | TODO
D-14 | P2 | No keyboard shortcuts — no J/K nav, no Cmd+Enter to submit. | app/(app)/ | Design/UX | Phase 1 | Lead FE | TODO
D-15 | P2 | OG image + favicon not configured — social shares have no preview. | app/layout.tsx | Design/SEO | Phase 1 | Designer | TODO
P-01 | P2 | Annual pricing toggle violates Landing-Page-Prompt-Pack.md (explicitly forbids it). | components/PricingToggle.tsx | Product/Gov | Phase 0 | PM | TODO
P-02 | P2 | Enterprise tier not in Decision-Log.md — violates AGENTS.md §1 locked-pricing rule. | BillingManager + Decision-Log.md | Product/Gov | Phase 0 | PM | TODO
P-03 | P2 | Schema enum drift — subscription_plan enum missing 'enterprise' value. | supabase/migrations/0001_init.sql | Product/Schema | Phase 0 | Lead BE | TODO
P-04 | P2 | TCPA compliance missing — no opt-in checkbox, no consent timestamp, no 10DLC registration. | OnboardingForm + send paths | Product/Compliance | Phase 6 | Sec Eng | TODO
P-05 | P2 | No data retention enforcement — policy says 90 days but no purge job exists. | lib/inngest/ | Product/Compliance | Phase 6 | Lead BE | TODO
P-06 | P2 | No audit log table — SOC2 readiness requires audit trail of every write operation. | supabase/migrations/ | Product/Compliance | Phase 6 | Sec Eng | TODO
P-07 | P2 | No DPA template — enterprise customers will require Data Processing Addendum. | /legal/ | Product/Legal | Phase 6 | PM | TODO
FB-11 | P3 | BeforeAfter slider uses placeholder stock images. | components/BeforeAfter.tsx | Frontend/Content | Phase 1 | Designer | TODO
FB-12 | P3 | TestimonialCarousel uses generic testimonials. | components/TestimonialCarousel.tsx | Frontend/Content | Phase 1 | PM | TODO
FB-13 | P3 | LiveDemo typewriter text is generic. | components/LiveDemo.tsx | Frontend/Content | Phase 1 | Designer | TODO
D-16 | P3 | LogoCarousel lacks hover animation (slight scale-up on hover). | LogoCarousel.tsx | Design/Motion | Phase 1 | Lead FE | TODO
D-17 | P3 | Buttons lack magnetic hover effect (premium touch). | components/ | Design/Motion | Phase 1 | Lead FE | TODO
D-18 | P3 | No page transition animations (route-level). | app/ | Design/Motion | Phase 1 | Lead FE | TODO
D-19 | P3 | Focus rings missing on several interactive elements. | components/ | Design/A11y | Phase 1 | Lead FE | TODO
D-20 | P3 | No prefers-reduced-motion support — animations always run. | components/ | Design/A11y | Phase 1 | Lead FE | TODO
D-21 | P3 | No prefers-color-scheme support — no auto dark mode. | app/globals.css | Design/A11y | Phase 1 | Lead FE | TODO
D-22 | P3 | Pricing toggle has no annual discount badge. | PricingToggle.tsx | Design/UX | Phase 1 | Designer | TODO
D-23 | P3 | Stat counter animation is linear, not eased. | StatCounter.tsx | Design/Motion | Phase 1 | Lead FE | TODO
D-24 | P3 | Mobile bottom tab bar missing. | app/(app)/layout.tsx | Design/Responsive | Phase 1 | Lead FE | TODO
D-25 | P3 | Footer lacks proper sitemap structure. | landing-page.html | Design/SEO | Phase 1 | Lead FE | TODO
D-26 | P3 | No 404 page illustration. | app/not-found.tsx (missing) | Design/UX | Phase 1 | Designer | TODO
D-27 | P3 | No 500 page illustration. | app/error.tsx (missing) | Design/UX | Phase 1 | Designer | TODO
BB-17 | P3 | Error messages not localized — hard-coded English. | all of app/api/ | Backend/I18n | Phase 5 | Lead BE | TODO
BB-18 | P3 | API responses not cached — repeated identical queries hit DB. | all of app/api/ | Backend/Perf | Phase 3 | Lead BE | TODO
BB-19 | P3 | No OpenAPI spec generated from route handlers. | lib/ | Backend/DX | Phase 3 | Lead BE | TODO
BB-20 | P3 | No automated API integration tests. | tests/ | Backend/QA | Phase 3 | Lead BE | TODO
BB-21 | P3 | Stripe customer portal not embedded — users can't self-manage subscription. | app/(app)/billing/ | Backend/Billing | Phase 3 | Lead BE | TODO
BB-22 | P3 | No webhook event log UI — debugging webhook issues requires DB access. | app/(app)/settings/ | Backend/DX | Phase 3 | Lead FE | TODO
BB-23 | P3 | No feature flag system — can't progressively roll out features. | lib/ | Backend | Phase 3 | Lead BE | TODO
BB-24 | P3 | No usage metering UI — users can't see their SMS/email/AI usage. | app/(app)/billing/ | Backend/Billing | Phase 3 | Lead FE | TODO
BB-25 | P3 | No public API — enterprise customers can't integrate programmatically. | app/api/ | Backend | Phase 4 | Lead BE | TODO
BB-26 | P3 | No API key management UI. | app/(app)/settings/ | Backend | Phase 4 | Lead FE | TODO
BB-27 | P3 | Resend bounce/complaint webhooks not handled — bad email addresses silently dropped. | lib/integrations/resend.ts | Backend | Phase 3 | Lead BE | TODO
BB-28 | P3 | Twilio inbound SMS not handled — STOP/UNSTOP keywords don't work. | lib/integrations/twilio.ts | Backend | Phase 3 | Lead BE | TODO
BB-29 | P3 | Twilio 10DLC campaign registration flow not built. | lib/integrations/twilio.ts | Backend/Compliance | Phase 6 | Lead BE | TODO
BB-30 | P3 | Google OAuth token refresh not handled — tokens expire in 1 hour. | lib/integrations/google-business-profile.ts | Backend | Phase 3 | Lead BE | TODO

## Feature Roadmap
Feature Roadmap — 10 Enterprise Modules
Sequenced for dependency order. Each module has owner, build effort, and target phase.
# | Module | Description | Build Effort | Cost | Phase | Owner | Priority | Status
M1 | Unified Review Inbox | Multi-channel inbox (Google + FB + Yelp + Trustpilot + Apple Maps) with threading, bulk actions, saved views, keyboard shortcuts, command palette. | 2 weeks | $30k | Phase 3 | Lead FE | P1
M2 | Multi-Channel Request Automation | Campaign builder, smart send-time, A/B testing, QR codes, WhatsApp, Apple Business Chat, TCPA-compliant opt-out. | 2 weeks | $30k | Phase 3 | Lead BE | P1
M3 | AI Reply + Brand Voice | Claude 3.5 pipeline with per-business brand voice training, approval workflow, multi-language, escalation detection, auto-post SLA. | 3 weeks | $45k | Phase 3 | Lead BE | P1
M4 | Sentiment & Topic Analytics | Per-review sentiment score, multi-label topic extraction, topic sentiment matrix, weekly trends, anomaly detection, NPS correlation. | 2 weeks | $30k | Phase 4 | Lead BE | P2
M5 | Widget & Testimonial Engine | Branded widgets (carousel, grid, masonry, slider, badge), video testimonials, case-study generator, white-label option. | 2 weeks | $25k | Phase 4 | Lead FE | P2
M6 | Multi-Tenant Agency Mode | White-label, client portal, per-seat pricing, 4-role RBAC, bulk actions, agency-level reporting. | 2 weeks | $35k | Phase 4 | Lead FE | P1
M7 | Competitor Intelligence | Weekly competitor snapshots (rating, velocity, sentiment), benchmark dashboard, gap analysis, Claude-generated strategy suggestions. | 2 weeks | $30k | Phase 4 | Lead BE | P2
M8 | Reporting & Alerts | Slack/Teams/email alerts, scheduled PDF reports (daily/weekly/monthly), executive + agency dashboards. | 1.5 weeks | $22k | Phase 4 | Lead FE | P2
M9 | Local SEO & Schema | JSON-LD Review schema generator, embed snippet, review velocity tracker, Claude-generated local SEO recommendations. | 1.5 weeks | $22k | Phase 5 | Lead BE | P3
M10 | Customer Experience Analytics | NPS, CSAT, CES surveys, correlation with reviews, customer journey map, detractor rescue flow. | 2 weeks | $28k | Phase 5 | Lead FE | P3

## Phase Timeline
24-Week Phase Timeline (Gantt-style)
Each cell = 1 week. Filled cell = active phase.
Phase | Focus | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Phase 0 | Stabilization (P0/P1 bugs, security, mock isolation)
Phase 1 | Design System (53 components, motion, dark mode)
Phase 2 | Auth & Multi-Tenant (Supabase Auth, RBAC, SSO, audit logs)
Phase 3 | Core Module Rebuild (Inbox, Requests, AI Reply, Billing webhooks)
Phase 4 | Enterprise Modules (Agency, Sentiment, Widgets, Competitor, Reporting)
Phase 5 | Automation & AI (Brand voice, multi-lang, smart routing, WhatsApp)
Phase 6 | Compliance & Launch (SOC2, GDPR, TCPA, pen test, beta, public launch)
MILESTONES
Event | Description | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
M1 | All P0/P1 bugs closed | bar: W2
M2 | Design system v1.0 shipped | bar: W5
M3 | Auth + RBAC live | bar: W7
M4 | End-to-end review → reply → post works | bar: W11
M5 | Agency mode + 5 enterprise modules live | bar: W18
M6 | Brand voice + multi-language + WhatsApp live | bar: W22
M7 | PUBLIC LAUNCH | bar: W24